## Slide 1
Game
Mechanic
Graphic
AI
GUI
Object
Character
Map
Effect
Collision
Gravity
Sound
Object
BGM
Story
Character
Rule
Sound

## Slide 2
Production | Work | Requie | SD | ED
Mechanic.Character | Player | Move, Skill, Combat, Interactive | 25/6/2025 | 
 | Crep | Move, Skill, Combat |  | 
 | Boss | Move, Skill, Combat |  | 
Mechanic.AI | Crep | Find Player to Chase, block dmg(possible) |  | 
 | Boss | Find Player, Skill’s logic |  | 
Mechanic.Rule | Quest | Complete quest to unlock area, |  | 
 | Quiz | Solve quizes to pass gates, reduce boss’s power, find key |  | 
Mechanic.Sound | BGM | Active when player get in area | 7/7/2025 | 
 | Object | Play when Interactive enviroment |  | 
Mechanic.Collision |  | Avilable | 25/6/2025 | 
Mechanic.Gravity |  | Apply to character, some object | 28/6/2025 | 
Graphic.GUI | Player’s stat | Hp bar, Mp bar, skill, item, buff, debuff | 28/6/2025 | 
 | Menu | New, continue(load), save |  | 
 | Setting | Graphic, sound |  | 
 | inventory | list item |  | 
 | Shop | List buy item |  | 
Graphic.Object.Map | Background |  |  | 
 | Ground |  | 25/6/2025 | 
 | Frontground |  |  | 
Graphic.Object.Character (Sprite + Animation) | Player |  | 5/7/2025 | 
 | Crep |  |  | 
 | Boss |  |  | 
Graphic.Object.Effect |  |  |  | 
Sound.BGM |  |  | 7/7/2025 | 
Sound.Object | Character |  |  | 
 | Environment |  |  | 
 | Physic Object |  |  | 
Story |  |  | 9/7/2025 | 
Total |  |  | 25/6/2025 | 20/9/2025
K
A
H
K
A
H
K
A
H
A
K
K
K
H
K
H
K

## Slide 3
1 Mechanic.Character.Player 14 days Wed 6/25/25Thu 9/18/25
2 Mechanic.Character.Crep 14 days Mon 9/1/25Thu 9/18/25
3 Mechanic.Character.Boss 14 days Mon 9/1/25Thu 9/18/25
4 Mechanic.AI.Crep 14 days Fri 9/19/25Wed 10/8/25 2
5 Mechanic.AI.Boss 14 days Fri 9/19/25Wed 10/8/25 3
6 Mechanic.Rule.Quest 14 days Thu 10/9/25Tue 10/28/25 1,2,3,4,5,10,11,18,20,21,22
7 Mechanic.Rule.Quiz 14 days Thu 10/9/25Tue 10/28/25 1,2,3,4,5,10,11,18,20,21,22
8 Mechanic.Sound.BGM 14 days Fri 9/19/25Wed 10/8/25 1,18,26
9 Mechanic.Sound.Object 14 days Thu 10/9/25Tue 10/28/25 19,20,21,22
10 Mechanic.Collision 14 days Mon 9/1/25Thu 9/18/25
11 Mechanic.Gravity 14 days Mon 9/1/25Thu 9/18/25
12 Graphic.GUI.Player's stat 14 days Fri 9/19/25Wed 10/8/25 1
13 Graphic.GUI.Menu 14 days Mon 9/1/25Thu 9/18/25
14 Graphic.GUI.Setting 14 days Fri 9/19/25Wed 10/8/25 13
15 Graphic.GUI.Inventory 14 days Thu 10/9/25Tue 10/28/25 12
16 Graphic.GUI.Shop 14 days Fri 9/19/25Wed 10/8/25 2
17 Graphic.Object.Map.Background 14 days Fri 9/19/25Wed 10/8/25 18
18 Graphic.Object.Map.Ground14 days Mon 9/1/25Thu 9/18/25
19 Graphic.Object.Map.FrontGround 14 days Fri 9/19/25Wed 10/8/25 18
20 Graphic.Object.Character.Player 14 days Mon 9/1/25Thu 9/18/25
21 Graphic.Object.Character.Crep 14 days Mon 9/1/25Thu 9/18/25
22 Graphic.Object.Character.Boss 14 days Mon 9/1/25Thu 9/18/25
23 Graphic.Object.Effect 14 days Mon 9/1/25Thu 9/18/25